## Test Scenerio
Project Name |  | waltonbd.com | Test Case Start Date | 2024-05-04 | Test Execution Start Date | - -
Module Name |  |  | Test Case End Date | 2024-07-04 | Test Execution End Date | - -
Epic |  |  | Test Case Developed By | Minhajur Rahman Mahi | Browser (tested) | Yes
Developer Name (Test Lead) |  |  | Test Case Reviewed By |  | Performance (tested) | No
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases | Number of Sucessful TestCase |  | Number of Failed TestCase | Out of scope | Not Executed
TS_001 |  | Verify the login functionality | P1 | 6 | 6 |  | 0 | 0 | 0
TS_002 |  | Verify the signup functionality | P1 | 7 | 6 |  | 1 |  | 0
TS_003 |  | Verify the working account functionality | P3 | 15 | 15 |  | 0 |  | 0
TS_004 |  | Verify the working of Search Functionality | P2 | 6 | 5 |  | 1 |  | 0
TS_005 |  | Verify the working of 'Add to Cart' Functionality | P2 | 5 | 5 |  | 0 |  | 0
TS_006 |  | Verify the working of Home Page Functionality | P2 | 11 | 11 |  | 0 |  | 0
TS_007 |  | Verify the working of Check Out Functionality | P2 | 7 | 7 |  | 0 |  | 0
TS_008 |  | Verify the working of Payment Method Functionality | P2 | 3 | 0 |  | 3 |  | 0
TS_009 |  | Verify the working of Wishlist Functionality | P5 | 4 | 4 |  | 0 |  | 0
TS_010 |  | Verify the working of 'Offer Zone' functionality | P4 | 3 | 3 |  | 0 |  | 0
TS_011 |  | Verify the working of 'Catagory' functionality | P2 | 12 | 12 |  | 0 |  | 0
TS_012 |  | Verify the working of 'Support' functionality | P4 | 7 | 7 |  | 0 |  | 0
|  |  |  | 86 | 81 |  | 5

## Test Summery Report
Test Case Report
Project Name | Waltonbd website
Module Name | Check Out From (Test Scenerio)
Feature Name
Test Case Version
Executed By | Minhajur Rahman Mahi
Written by | Minhajur Rahman Mahi
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out of Scope | Total Test Cases
Test Case | 81 | 5 | 0 | 0 | 86
LIMITATIONS
Document |  | Recived |  | Useful
PRD |  | NO
USER STORY |  | NO
SRS |  | NO
| Testing Type in Scope | Description
| Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Integration Testing
Negative Testing
| Usability Testing | Test application from user friendliness perspective.
| Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Boundary Value Tesing
Risk Based Testing or Regression Testing

## Bug Report
Bug Reporting | Bug Reporting
Serial : 01 | Serial : 02
Issue : Payment segement isnt clickable in order to perform any functionality | Issue : Navigation failed while taking the user from homepage to payment segment
Reproducing Steps: | Reproducing Steps:
1.Goto the waltonbd 2.Go to homepage 3.Click "payment" the lower middle corner segment | 1.Goto the waltonbd 2.Go to homepage 3.Click "payment" the lower middle corner segment
Environment: Production | Environment: Production
Module: Payment | Module: Payment
Test Case ID : TCP_001 | Test Case ID : TCP_002
Priority: P2 | Priority: P2
Severity: | Severity:
Bug SS: https://prnt.sc/3jfefmXxpi4W | Bug SS: https://prnt.sc/3jfefmXxpi4W
Expected: The payment segment should be clickable | Expected: It should naviage from homepage to payment
Responsible QA: Minhajur Rahman Mahi | Responsible QA: Minhajur Rahman Mahi
Bug Reporting
Serial : 03
Issue : Taking invalid first name while giving credential for signup
Reproducing Steps:
1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "register"" button 4.Click First Name field
Environment: Production
Module: Signup
Test Case ID : TCS_007
Priority: P3
Severity:
Bug SS: https://prnt.sc/hzZiNqjpGxRU
Expected: Should only take valid names
Responsible QA: Minhajur Rahman Mahi

## Login
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCL_001 | (TS_001) Login Functionality | Checking the 'login' button working properly or not | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "Login" button | None | Should clickable the "Login" button | Found as per the expectation | P1 | PASS
TCL_002 | (TS_001) Login Functionality | Checking the 'E-Mail Address' field mail validity | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "E-mail Address" field | None | E-Mail address field should be clickable and take valid email address | Found as per the expectation | P1 | PASS
TCL_003 | (TS_001) Login Functionality | Checking the 'password' field encryption | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "Password" field | None | Password typed in the field should be encrypted | Found as per the expectation | P1 | PASS
TCL_004 | (TS_001) Login Functionality | Checking the 'forget password' function is working properly or not | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "forget password" option | None | Should take the user in different page to verify mail address | Found as per the expectation | P1 | PASS
TCL_005 | (TS_001) Login Functionality | Checking the error messege displayed after entering only E-mail address | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "E-mail" field 4.Click "Login" button | None | Should show the warning display after entering one E-mail address | Found as per the expectation | P1 | PASS
TCL_006 | (TS_001) Login Functionality | Checking the error messege displayed after entering wrong password | 1. Goto the waltonbd 2. Click on the "Account" button in the left upper corner 3.Click "password" field | None | Should show the warning display after entering one wrong password | Found as per the expectation | P1 | PASS

## Signup
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCS_001 | (TS_002) Signup Functionality | Checking wheaher the user name working correctly | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "register"" button 4.Click First Name and then Last Name | None | Should be clickable and talking user name correctly | Found as per the expectation | P1 | PASS
TCS_002 | (TS_002) Signup Functionality | Checking whethear the gmail is working properly | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "register"" button 4.Click gmail | None | Should be clickable and talking valid gmail | Found as per the expectation | P1
TCS_003 | (TS_002) Signup Functionality | Checking whether the Phone number field is responsive | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "Phone Number"" button 4.Click phone | None | Should be clickable and typeable also | Found as per the expectation | P1 | PASS
TCS_004 | (TS_002) Signup Functionality | Checking whether the password field is responsive | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "Password" field | None | Should be clickable and typeable also to take only the strong password | Found as per the expectation | P1
TCS_005 | (TS_002) Signup Functionality | Checking the password and confirm password are working properly or not | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "Password" field 4.Click "Confrim Password" field | None | Both of the type password should be same | Found as per the expectation | P1 | PASS
TCS_006 | (TS_002) Signup Functionality | Checking the strong password protocol is being maintained or not | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "register"" button 4.Click password field | None | Password must contain atleast one uppercase, one lower,one digit and one special character | Found as per the expectation | P1 | PASS
TCS_007 | (TS_002) Signup Functionality | Checking wheaher the First name takes an any invalid name | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "register"" button 4.Click First Name field | None | First name filed should not take any invalid name | Found as not per the expectation | P1 | FAIL | bug screenshot

## Account
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCA_001 | (TS_003) My Account Functionality | Verify navigating to 'My Account' page on login | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button | None | User should be able to login and taken to 'My Account' page | Found as per the expectation | P3 | PASS
TCA_002 | (TS_003) My Account Functionality | Verify clicking all account information related fields are clickable or not | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button | None | Should show the relevant information of the user | Found as per the expectation | P3 | PASS
TCA_003 | (TS_003) My Account Functionality | Verify checking edit account information functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button | None | Should enable the user to edit its given information | Not Found as per expectation | P3 | PASS
TCA_004 | (TS_003) My Account Functionality | Verify checking the change pasword functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the change password | None | Should enable the user to change his/her password | Found as per the expectation | P3 | PASS
TCA_005 | (TS_003) My Account Functionality | Verify checking the address book entry functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the vciew privacy book segment | None | Should enable the user to change address | Found as per the expectation | P3 | PASS
TCA_006 | (TS_003) My Account Functionality | Verify checking view policy functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the view policy segment | None | Should show the user view policy | Found as per the expectation | P3 | PASS
TCA_007 | (TS_003) My Account Functionality | Verify checking "modify wishlist functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the whishlist segment | None | Should provide the information of wishlist | Found as per the expectation | P3 | PASS
TCA_008 | (TS_003) My Account Functionality | Verify checking "logout" functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Then click "logout" button | None | User should be able to logout from account | Found as per the expectation | P3 | PASS
TCA_008 | (TS_003) My Account Functionality | Verify clcking the order history | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click order history segment | None | User should be able to previous search history | Found as per the expectation | P3 | PASS
TCA_009 | (TS_003) My Account Functionality | Verify clicking the reward points functionality are clickable or not | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the reward point segment | None | User should see the reward points from buying products | Found as per the expectation | P3 | PASS
TCA_010 | (TS_003) My Account Functionality | Verify clicking the return request functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the return request segment | None | Enable the user to see the return request | Found as per the expectation | P3 | PASS
TCA_011 | (TS_003) My Account Functionality | Verify checking "Wish List" functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the wish List segment | None | Should enable the user to see the wish list segment | Found as per the expectation | P3 | PASS
TCA_012 | (TS_003) My Account Functionality | Verify chekcing the "transaction" functionality | 1. Goto the waltonbd website 2. Click on the ""My Account"" button in the upper right corner 3.Click "login"" button 4.Click the transaction segment | None | Should enable the user to see the transactions | Found as per the expectation | P3 | PASS

## Search
TS_R004
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCSE_001 | (TS_004) Search Functionality | Verify checking the search bar is clickable or not | 1.Goto the waltonbd 2.Click on the Search field | None | Searched product should be displayed in the search results | Found as per the expectation | P2 | PASS
TCSE_002 | (TS_004) Search Functionality | Verify checking the search bar works properly on the basis of desired items or not | 1.Goto the waltonbd 2.Enter Any valid Product on Search Box 3.Enter the search field | Product Name: Fan | We cannot find any matches for your search term' should be displayed in the Search Results page' | Found as per the expectation | P2 | PASS
TCSE_003 | (TS_004) Search Functionality | Verify searching without placing any placing any product name | 1.Goto the waltonbd 2.Press enter the search field without inserting any product name | None | Search Button should not work for empty search box | Found as per the expectation | P2 | PASS
TCSE_004 | (TS_004) Search Functionality | Verify searching wheather it able to show multiple product | 1.Goto the waltonbd 2.Enter Any valid Product on Search Box 3.Enter the search field | Product Name: Clock | Searched product should be displayed in the search results | Found as per the expectation | P2 | PASS
TCSE_005 | (TS_004) Search Functionality | Verify searching the invalid products name | 1.Goto the waltonbd 2.Enter Any valid Product on Search Box 3.Enter the search field | Product Name: @ | No product and Invalid text should be shown | Found not as per the expectation | P2 | FAIL | Bug SS
TCSE_006 | (TS_004) Search Functionality | Verify searching history after searching muliple products | 1.Goto the waltonbd 2.Enter the search field to see the previous search result | Product Name: Fan | Previous search result should be shown | Found not as per the expectation | P2 | PASS

## Add to Cart
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCSC_001 | (TS_R005) Add to Cart Functionality | Verify clicking the "shopping cart" is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | None | Should be clickable to ensure functionality | Found as per the expectation | P2 | PASS
TCSC_002 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | product name:Dry-iron | Should add the products the user want to buy | Found as per the expectation | P2 | PASS
TCSC_003 | (TS_R005) Add to Cart Functionality | Verify checking the previous product is saved in the cart or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | None | Should show the previously added product on cart | Found as per the expectation | P2 | PASS
TCSC_004 | (TS_R005) Add to Cart Functionality | Verify adding the product to Cart from the Products displayed in the 'Top picks for you' section of Home page | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | product name:Takyon 1 | Should enable the user to add proudct to cart from initital homepage | Found as per the expectation | P2 | PASS
TCSC_004 | (TS_R005) Add to Cart Functionality | Verify clicking buy on the product wheather it allows without login or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | none | Should not enable the user to add product on cart without login | Found as per the expectation | P2 | PASS
TCSC_004 | (TS_R005) Add to Cart Functionality | Verify navigating from Home page to shopping-cart | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | None | Should take the user from homepage to shopping-cart | Found as per the expectation | P2 | PASS
TCSC_005 | (TS_R005) Add to Cart Functionality | Verify checking multiple products can be added to cart or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | None | Should enable the user to add multiple products on the cart | Found as per the expectation | P2 | PASS
TCSC_005 | (TS_R005) Add to Cart Functionality | Verify checking single products can be added to cart or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "Shopping-Cart" the upper right side | product name:Passion Bx | Should enable the user to add only one product | Found as per the expectation | P2 | PASS

## Home Page
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCH_001 | (TS_006) Home Page Functionality | Verify clicking each of the catagory wheather it navigates to that specific catagory | 1.Goto the Daraz App 2.Click"My Cart" button 3.Click back/home button | Search Product Name : Samsung | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_002 | (TS_006) Home Page Functionality | Verify checking wheather the carousal is working properly or not | 1.Goto the Daraz App 2.Click "Account" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_003 | (TS_006) Home Page Functionality | Verify checking wheather homepage shows various types of products or not | 1.Goto the Daraz App 2.Click "Messages" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_004 | (TS_006) Home Page Functionality | Verify checking the shown product on the homepage is accecssable or not | 1.Goto the Daraz App 2.Click "Discover" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_005 | (TS_006) Home Page Functionality | Verfy checking that user can login from homepage or not | 1.Goto the Daraz App 2.Click "Slide Bar" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_006 | (TS_006) Home Page Functionality | Verify navigating from homepage to "wish list" | 1.Goto the Daraz App 2.Click "Any 3 for bdt 599" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_007 | (TS_006) Home Page Functionality | Verify navigating from homepage to "add to cart" | 1.Goto the Daraz App 2.Click "Categories" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_008 | (TS_006) Home Page Functionality | Verify navigating from homepage to "checkout" | 1.Goto the Daraz App 2.Click "Daraz Coins'" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_009 | (TS_006) Home Page Functionality | Verify navigating from homepage to "Apply to Kisti" | 1.Goto the Daraz App 2.Click "Quick Topup'" button 3.Click back/home button | None | User should be taken to Home page | Found as per the expectation | P2 | PASS
TCH_010 | (TS_006) Home Page Functionality | Verify navigating from homepage to all the sub segment of "offer zone" | 1.Goto the Daraz App 2.Click "Set your delivery location" field | None | 1.Field Should be clickable 2.Should Hover text"Set your delivery field" | 1.Found as per the expectation 2.Found as per the expectation | P2 | PASS
TCH_011 | (TS_006) Home Page Functionality | verify checking try new site is accessable or not | 1.Goto the Daraz App 2.Click "Set your delivery location" field 3.Click "use my current location" 4.Give acces permission for GPS | None | User current location should be accessable automatically | Not Found as per expectation | P2 | PASS

## Checkout
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCC_001 | (TS_007) My Order Functionality | Verify checking wheather the checkout steps are shown or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Should show the user of specific steps to buy | Found as per the expectation | P2 | PASS
TCC_002 | (TS_007) My Order Functionality | Checking whether all the segments of "checkout" is clickable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Steps needed to be clickable and navigating to desired space | Found as per the expectation | P2 | PASS
TCC_003 | (TS_007) My Order Functionality | Checking wheather billing details is working properly or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | User should see the amount of billing products at once with detail | Found as per the expectation | P2 | PASS
TCC_004 | (TS_007) My Order Functionality | Verify checking wheathher "delivery details" is shown or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Should show the user of derilivery details of their respective product | Found as per the expectation | P2 | PASS
TCC_005 | (TS_007) My Order Functionality | Verify checking weather "payment" segment is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Should enable the user to select the paymnet method | Found as per the expectation | P2 | PASS
TCC_006 | (TS_007) My Order Functionality | Verify checking weather "delivery" segment is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Should enable the to see the delivery details | Found as per the expectation | P2 | PASS
TCC_007 | (TS_007) My Order Functionality | Verify checking weather "confirm" segment is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "checkout" the upper right corner | None | Should show the confirmation messege and complete the order process | Found as per the expectation | P2 | PASS

## Payment
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCP_001 | (TS_008) My Returns Functionality | Verify wheather the payment method is clickable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "payment" the lower middle corner segment | None | Should be clickable to navigate to functionality | Found not as per the expectation | P2 | FAIL | Bug SS
TCP_002 | (TS_008) My Returns Functionality | Verify navigating "Home page" to payment method | 1.Goto the waltonbd 2.Go to homepage 3.Click "payment" the lower middle corner segment | None | Should take the user from homepage to payment method | Found not as per the expectation | P2 | FAIL | Bug SS
TCP_003 | (TS_008) My Returns Functionality | Verify checking wheather the payment segment is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click "payment" the lower middle corner segment | None | Should enable the user to do the payment for the product | Found not as per the expectation | P2 | FAIL

## Wishlist
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCW_001 | (TS_009) Wish List Functionality | Verify Adding product to 'Wishlist' from Product Page | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "wishlist" the upper right corner | None | Should added to wishlist | Found as per the expectation | P5 | PASS
TCW_002 | (TS_009) Wish List Functionality | Verify Wishlist button fuctionality | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "wishlist" the upper right corner | None | Button should be workable and after clicking button its color have to be changed | Found as per the expectation | P5 | PASS
TCW_003 | (TS_009) Wish List Functionality | Verify checking the wishlist is clickable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "wishlist" the upper right corner | None | Should open to my wishlist page | Found as per the expectation | P5 | PASS
TCW_004 | (TS_009) Wish List Functionality | Verify accessing "wishlist" without login | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "wishlist" the upper right corner | None | Should not navigate to wishlist without login to to account | Found as per the expectation | P5 | PASS

## Offer Zone
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCO_001 | (TS_010) Offer Zone functionality | Verify checking each of the segment is clickable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should be clickable | Found as per the expectation | P4 | PASS
TCO_002 | (TS_010) Offer Zone functionality | Verify checking "store locator" navigating from "Homepage" or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should navigate from home page to store locator | Found as per the expectation | P4 | PASS
TCO_003 | (TS_010) Offer Zone functionality | Verify checking "sales out" functionlity | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Sales out functionality should work properly | Found as per the expectation | P4 | PASS

## Catagory page
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCC_001 | (TS_011) Product Page Functionality | Verify navigating to 'Catagory Page' from Homepage | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to 'Product' page | Found as per the expectation | P2 | PASS
TCC_002 | (TS_011) Product Page Functionality | Verify navigating to 'Catagory Page' from Homepage | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to 'Product' page | Found as per the expectation | P2 | PASS
TCC_003 | (TS_011) Product Page Functionality | Verify navigating to 'Catagory Page' from account segment | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to 'Product' page | Found as per the expectation | P2 | PASS
TCC_004 | (TS_011) Product Page Functionality | Verify navigating to 'Catagory Page' from shopping cart | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to 'Product' page | Found as per the expectation | P2 | PASS
TCC_005 | (TS_011) Product Page Functionality | Verify checking the each of the dropdown segment of specific 'Catagory' | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to 'Product' page | Found as per the expectation | P2 | PASS
TCC_006 | (TS_011) Product Page Functionality | Verify checking the specific product is accessable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should open to "Catagory" page | Found as per the expectation | P2 | PASS
TCC_007 | (TS_011) Product Page Functionality | Verify clicking "Buy Now" functionality is working or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should take the user to shopping cart | Found as per the expectation | P2 | PASS
TCC_008 | (TS_011) Product Page Functionality | Verify clicking the product details is visiable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Shoould show the user product related details | Found as per the expectation | P2 | PASS
TCC_009 | (TS_011) Product Page Functionality | Verify checking where product is enable the user is to add in the wishlist or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | User should be able to add the product on the wishlist | Found as per the expectation | P2 | PASS
TCC_010 | (TS_011) Product Page Functionality | Verify checking the specific product is being added on the comparison or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Should enable the user to do the comparison between products | Found as per the expectation | P2 | PASS
TCC_011 | (TS_011) Product Page Functionality | Verify checking wheather the product is being add on the "add to cart" or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | User should be able to their desired product from product page to shopping cart | Found as per the expectation | P2 | PASS
TCC_012 | (TS_011) Product Page Functionality | Verify checking wheather the product is being sorted according alphabet or not | 1.Goto the waltonbd 2.Go to homepage 3.Click on the "Specific product" | None | Product should be shorted accourding to the alphabhetical and numerical order | Found as per the expectation | P2 | PASS

## Support
Test Case ID | Test Scenario | Test Case Description | Test Case Step | Test Data | Expected Result | Actual Result | Priority | Final Status | Bug Screenshot
TCS_001 | (TS_012) Support functionality | Verify checking each of the segment is clickable or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should be clickable | Found as per the expectation | P4 | PASS
TCS_002 | (TS_012) Support functionality | Verify checking "store locator" navigating from "Homepage" or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should navigate from home page to store locator | Found as per the expectation | P4 | PASS
TCS_003 | (TS_012) Support functionality | Verify checking "sales out" functionlity | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Sales out functionality should work properly | Found as per the expectation | P4 | PASS
TCS_004 | (TS_012) Support functionality | Verify checking "Customer care" functionality | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should show the places of customer care center | Found as per expectation | P4 | PASS
TCS_005 | (TS_012) Support functionality | Verify checking "Service request" is navigating to desired page or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should take some info to give user the service request | Found as per the expectation | P4 | PASS
TCS_006 | (TS_012) Support functionality | Verify checking "Service status" is navigating to desired page or not | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should show the requested service status of the user | Found as per the expectation | P4 | PASS
TCS_007 | (TS_012) Support functionality | Verify checking "Career" functionality | 1.Goto the waltonbd 2.Go to homepage 3.Click dropdown "supporton the upper right corner. | None | Should show the take employee cv and subscription | Found as per the expectation | P4 | PASS